## UNIFIED_TASKS
ID | Catégorie | Tâche | Responsable | Début | Fin | % Av. | Statut | Label | Mendatories
W001 | WEBSITE | Infra hosting setup (99.9% uptime) | Hatem/Firas | 07/12/2025 | 15/12/2025 | 0 | Non démarré
W002 | WEBSITE | Domain + SSL/TLS | Hatem/Firas | 07/12/2025 | 08/12/2025 | 0 | Non démarré
W003 | WEBSITE | CMS selection & setup | Hatem/Firas | 08/12/2025 | 15/12/2025 | 0 | Non démarré
W004 | WEBSITE | Homepage design | Farouk/Yacine | 07/12/2025 | 20/12/2025 | 0 | Non démarré
W005 | WEBSITE | About Calimero page | Farouk/Yacine | 20/12/2025 | 27/12/2025 | 0 | Non démarré
W006 | WEBSITE | Watch Clips Library (design) | Farouk/Yacine | 27/12/2025 | 10/01/2026 | 0 | Non démarré
W007 | WEBSITE | AI Portal (Talk to Calimero) | Nourey/Hatem | 10/01/2026 | 20/01/2026 | 0 | Non démarré |  | API integration pending
W008 | WEBSITE | Merchandise Store design | Farouk/Yacine | 20/01/2026 | 31/01/2026 | 0 | Non démarré |  | Catalogue eCommerce
W009 | WEBSITE | Community Hub page | Farouk/Yacine | 31/01/2026 | 07/02/2026 | 0 | Non démarré |  | UGC data
W010 | WEBSITE | Memes Gallery page | Farouk/Yacine | 31/01/2026 | 07/02/2026 | 0 | Non démarré
W011 | WEBSITE | 5 Easter eggs implementation | Hamza | 15/01/2026 | 31/01/2026 | 0 | Non démarré
W012 | WEBSITE | Multilingual setup (4 languages) | Hatem/Firas | 01/01/2026 | 15/01/2026 | 0 | Non démarré
W013 | WEBSITE | WCAG 2.1 AA accessibility audit | Hatem/Nourey | 15/01/2026 | 22/01/2026 | 0 | Non démarré
W014 | WEBSITE | GA4 + analytics integration | Hatem/Firas | 01/01/2026 | 15/01/2026 | 0 | Non démarré
W015 | WEBSITE | Payment gateway integration (2 min) | Hatem/Firas | 15/01/2026 | 31/01/2026 | 0 | Non démarré |  | PCI DSS compliance
W016 | WEBSITE | Daily backup system (30-day retention) | Hatem/Firas | 15/12/2025 | 22/12/2025 | 0 | Non démarré
W017 | WEBSITE | SEO foundations (meta/schema/sitemap) | Hatem/Nourey | 15/12/2025 | 31/12/2025 | 0 | Non démarré
W018 | WEBSITE | Performance optimization (3s load) | Hatem/Firas | 15/01/2026 | 31/01/2026 | 0 | Non démarré
W019 | WEBSITE | Admin panel development | Hatem/Firas | 22/12/2025 | 07/01/2026 | 0 | Non démarré
W020 | WEBSITE | Website testing & QA | Hatem | 31/01/2026 | 07/02/2026 | 0 | Non démarré
S001 | SOCIAL_MEDIA | 30+ page social strategy | Ismail/Farah/Hatem/Souleima | 07/12/2025 | 15/12/2025 | 0 | Non démarré | Global
S002 | SOCIAL_MEDIA | Brand voice & tone guide | Ismail/Farah/Souleima | 07/12/2025 | 15/12/2025 | 0 | Non démarré | Global
S003 | SOCIAL_MEDIA | Instagram account creation & optimization | Nourey/Souleima | 15/12/2025 | 22/12/2025 | 0 | Non démarré | Instagram
S004 | SOCIAL_MEDIA | TikTok account creation & optimization | Hamza/Souleima | 15/12/2025 | 22/12/2025 | 0 | Non démarré | TikTok
S005 | SOCIAL_MEDIA | Twitter/X account creation & optimization | Ismail/Souleima | 15/12/2025 | 22/12/2025 | 0 | Non démarré | Twitter/X
S006 | SOCIAL_MEDIA | YouTube Shorts channel setup | Hamza/Souleima | 15/12/2025 | 22/12/2025 | 0 | Non démarré | YouTube
S007 | SOCIAL_MEDIA | Community guidelines document | Ismail/Souleima | 15/12/2025 | 22/12/2025 | 0 | Non démarré | Global
S008 | SOCIAL_MEDIA | 3-month editorial calendar (45+ posts) | Ismail/Farah/Souleima | 22/12/2025 | 31/12/2025 | 0 | Non démarré | Global
S009 | SOCIAL_MEDIA | 12+ teaser content creation | Nourey/Hamza | 22/12/2025 | 31/12/2025 | 0 | Non démarré | Global
S010 | SOCIAL_MEDIA | UGC curation framework | Ismail/Souleima | 22/12/2025 | 31/12/2025 | 0 | Non démarré | Global
S011 | SOCIAL_MEDIA | Hashtag ecosystem (brand/campaign/trending) | Ismail/Souleima | 22/12/2025 | 31/12/2025 | 0 | Non démarré | Global
S012 | SOCIAL_MEDIA | Instagram posting (4/week + daily Stories) | Souleima | 08/01/2026 | 07/03/2026 | 0 | Non démarré | Instagram
S013 | SOCIAL_MEDIA | TikTok posting (5 videos/week) | Hamza/Souleima | 08/01/2026 | 07/03/2026 | 0 | Non démarré | TikTok
S014 | SOCIAL_MEDIA | Twitter/X posting (6 posts/week) | Ismail/Souleima | 08/01/2026 | 07/03/2026 | 0 | Non démarré | Twitter/X
S015 | SOCIAL_MEDIA | YouTube Shorts (3 videos/week) | Hamza/Souleima | 08/01/2026 | 07/03/2026 | 0 | Non démarré | YouTube
S016 | SOCIAL_MEDIA | Monthly performance analysis | Ismail/Farah | 31/12/2025 | 07/01/2026 | 0 | Non démarré | Global
S017 | SOCIAL_MEDIA | Monthly performance analysis M2 | Ismail/Farah | 31/01/2026 | 07/02/2026 | 0 | Non démarré | Global
S018 | SOCIAL_MEDIA | Monthly performance analysis M3 | Ismail/Farah | 28/02/2026 | 07/03/2026 | 0 | Non démarré | Global
C001 | COMMUNITY_CAMPAIGN | Daily community management setup | Ismail/Souleima | 07/12/2025 | 15/12/2025 | 0 | Non démarré | Community
C002 | COMMUNITY_CAMPAIGN | #ItsNotFair campaign strategy | Ismail/Souleima/Nourey | 15/01/2026 | 31/01/2026 | 0 | Non démarré | Campaign
C003 | COMMUNITY_CAMPAIGN | 20+ creative assets (visuals/templates) | Farouk/Yacine | 01/02/2026 | 15/02/2026 | 0 | Non démarré | Campaign
C004 | COMMUNITY_CAMPAIGN | Meme contest system design | Ismail/Souleima | 01/02/2026 | 15/02/2026 | 0 | Non démarré | Campaign
C005 | COMMUNITY_CAMPAIGN | Submission workflow setup | Ismail/Hatem | 01/02/2026 | 15/02/2026 | 0 | Non démarré | Campaign
C006 | COMMUNITY_CAMPAIGN | Contest judging framework | Ismail/Souleima | 15/02/2026 | 22/02/2026 | 0 | Non démarré | Campaign
C007 | COMMUNITY_CAMPAIGN | Leaderboard design & implementation | Farouk/Yacine | 15/02/2026 | 28/02/2026 | 0 | Non démarré | Campaign
C008 | COMMUNITY_CAMPAIGN | Campaign tracking dashboard | Ismail/Farah | 22/02/2026 | 07/03/2026 | 0 | Non démarré | Campaign
C009 | COMMUNITY_CAMPAIGN | Reddit micro-community r/Calimero | Ismail/Souleima | 07/01/2026 | 31/01/2026 | 0 | Non démarré | Community
C010 | COMMUNITY_CAMPAIGN | Reddit micro-community r/CalimeroMemes | Ismail/Souleima | 07/01/2026 | 31/01/2026 | 0 | Non démarré | Community
C011 | COMMUNITY_CAMPAIGN | Weekly 9gag submissions | Souleima/Hamza | 08/01/2026 | 07/03/2026 | 0 | Non démarré | Community
C012 | COMMUNITY_CAMPAIGN | Daily community moderation (8am-6pm CET) | Souleima | 08/01/2026 | 07/03/2026 | 0 | Non démarré | Community
C013 | COMMUNITY_CAMPAIGN | Minimum 50 interactions/month tracking | Ismail/Souleima | 31/12/2025 | 07/01/2026 | 0 | Non démarré | Community
C014 | COMMUNITY_CAMPAIGN | Interaction tracking M2 | Ismail/Souleima | 31/01/2026 | 07/02/2026 | 0 | Non démarré | Community
C015 | COMMUNITY_CAMPAIGN | Interaction tracking M3 | Ismail/Souleima | 28/02/2026 | 07/03/2026 | 0 | Non démarré | Community
I001 | INFLUENCERS_MEMES | 100+ micro-influencers mapping EU | Farah/Hatem/Souleima | 07/12/2025 | 31/12/2025 | 0 | Non démarré | Influencers
I002 | INFLUENCERS_MEMES | 50+ meme pages mapping | Farah/Hatem/Souleima | 07/12/2025 | 31/12/2025 | 0 | Non démarré | Memes
I003 | INFLUENCERS_MEMES | Influencer partnership negotiations | Farah/Hatem/Souleima | 01/01/2026 | 31/01/2026 | 0 | Non démarré | Influencers
I004 | INFLUENCERS_MEMES | 20+ influencer partnerships finalized | Farah/Souleima | 31/01/2026 | 07/02/2026 | 0 | Non démarré | Influencers
I005 | INFLUENCERS_MEMES | Meme page partnership negotiations | Farah/Hatem/Souleima | 01/02/2026 | 15/02/2026 | 0 | Non démarré | Memes
I006 | INFLUENCERS_MEMES | 10+ meme page partnerships finalized | Farah/Souleima | 15/02/2026 | 28/02/2026 | 0 | Non démarré | Memes
I007 | INFLUENCERS_MEMES | 10 co-created viral content formats | Nourey/Hamza | 15/01/2026 | 07/02/2026 | 0 | Non démarré | Content | Partner input
I008 | INFLUENCERS_MEMES | Creator drop calendar (2 months) | Farah/Souleima | 01/02/2026 | 07/03/2026 | 0 | Non démarré | Planning
I009 | INFLUENCERS_MEMES | Influencer analytics dashboard | Farah/Hatem | 15/02/2026 | 28/02/2026 | 0 | Non démarré | Reporting
I010 | INFLUENCERS_MEMES | Monthly influencer report M1 | Farah/Souleima | 31/12/2025 | 07/01/2026 | 0 | Non démarré | Reporting
I011 | INFLUENCERS_MEMES | Monthly influencer report M2 | Farah/Souleima | 31/01/2026 | 07/02/2026 | 0 | Non démarré | Reporting
I012 | INFLUENCERS_MEMES | Monthly influencer report M3 | Farah/Souleima | 28/02/2026 | 07/03/2026 | 0 | Non démarré | Reporting
P001 | PAID_ADS_PR | Complete ad strategy (Meta/TikTok/YouTube) | Farah/Souleima | 07/12/2025 | 22/12/2025 | 0 | Non démarré | Ads
P002 | PAID_ADS_PR | Audience segmentation & lookalike models | Farah/Souleima | 22/12/2025 | 31/12/2025 | 0 | Non démarré | Ads
P003 | PAID_ADS_PR | Pixel setup & tracking implementation | Farah/Hatem | 07/12/2025 | 22/12/2025 | 0 | Non démarré | Ads
P004 | PAID_ADS_PR | 15 Meta ad creatives | Farouk/Yacine | 22/12/2025 | 15/01/2026 | 0 | Non démarré | Ads
P005 | PAID_ADS_PR | 15 TikTok ad creatives | Farouk/Yacine | 22/12/2025 | 15/01/2026 | 0 | Non démarré | Ads
P006 | PAID_ADS_PR | 15 YouTube ad creatives | Farouk/Yacine | 22/12/2025 | 15/01/2026 | 0 | Non démarré | Ads
P007 | PAID_ADS_PR | Retargeting flows setup | Farah/Hatem | 15/01/2026 | 22/01/2026 | 0 | Non démarré | Ads
P008 | PAID_ADS_PR | Ads go live (Meta/TikTok/YouTube) | Farah/Souleima | 08/01/2026 | 15/01/2026 | 0 | Non démarré | Ads
P009 | PAID_ADS_PR | Weekly ad optimization | Farah/Souleima | 15/01/2026 | 07/03/2026 | 0 | Non démarré | Ads
P010 | PAID_ADS_PR | Monthly ad performance report | Farah/Souleima | 31/12/2025 | 07/01/2026 | 0 | Non démarré | Reporting
P011 | PAID_ADS_PR | Monthly ad performance report M2 | Farah/Souleima | 31/01/2026 | 07/02/2026 | 0 | Non démarré | Reporting
P012 | PAID_ADS_PR | Monthly ad performance report M3 | Farah/Souleima | 28/02/2026 | 07/03/2026 | 0 | Non démarré | Reporting
P013 | PAID_ADS_PR | PR strategy document | Ismail/Farah | 07/12/2025 | 22/12/2025 | 0 | Non démarré | PR
P014 | PAID_ADS_PR | 3 press releases drafted | Ismail/Farah | 22/12/2025 | 31/01/2026 | 0 | Non démarré | PR
P015 | PAID_ADS_PR | Media outreach (50 outlets) | Farah/Souleima | 07/12/2025 | 31/01/2026 | 0 | Non démarré | PR
P016 | PAID_ADS_PR | 2 long-form interviews (1500+ words) | Ismail | 01/01/2026 | 31/01/2026 | 0 | Non démarré | PR
P017 | PAID_ADS_PR | Full media kit creation | Nourey/Ismail | 15/01/2026 | 31/01/2026 | 0 | Non démarré | PR
P018 | PAID_ADS_PR | Monthly media & buzz report | Ismail/Farah | 31/12/2025 | 07/01/2026 | 0 | Non démarré | Reporting
A001 | AI_APP | AI App UX/UI design (iOS/Android) | Farouk/Yacine | 07/12/2025 | 15/01/2026 | 0 | Non démarré | Both
A002 | AI_APP | Emotional dialogue engine development | Hatem/Firas | 15/12/2025 | 15/01/2026 | 0 | Non démarré | Backend
A003 | AI_APP | 20 original bedtime stories creation | Hamza | 22/12/2025 | 31/01/2026 | 0 | Non démarré | Content
A004 | AI_APP | Text-to-Speech (TTS) integration | Hatem/Firas | 15/01/2026 | 22/01/2026 | 0 | Non démarré | Backend
A005 | AI_APP | Speech-to-Text (STT) integration | Hatem/Firas | 15/01/2026 | 22/01/2026 | 0 | Non démarré | Backend
A006 | AI_APP | Gamification system (25+ badges) | Hatem/Firas | 22/01/2026 | 31/01/2026 | 0 | Non démarré | Backend
A007 | AI_APP | Daily streaks feature | Hatem/Firas | 22/01/2026 | 31/01/2026 | 0 | Non démarré | Backend
A008 | AI_APP | Voice pack marketplace (5+ variations) | Hatem/Firas | 31/01/2026 | 07/02/2026 | 0 | Non démarré | Backend
A009 | AI_APP | Rewards system (convertible to discounts) | Hatem/Firas | 31/01/2026 | 07/02/2026 | 0 | Non démarré | Backend
A010 | AI_APP | Parental controls setup | Hatem/Firas | 01/02/2026 | 15/02/2026 | 0 | Non démarré | Backend | COPPA compliance
A011 | AI_APP | Screen time limits implementation | Hatem/Firas | 01/02/2026 | 08/02/2026 | 0 | Non démarré | Backend
A012 | AI_APP | Age-appropriate content filters | Hatem/Firas | 08/02/2026 | 15/02/2026 | 0 | Non démarré | Backend
A013 | AI_APP | GDPR privacy framework | Hatem/Ismail | 22/12/2025 | 31/12/2025 | 0 | Non démarré | Compliance
A014 | AI_APP | COPPA compliance setup | Hatem/Ismail | 22/12/2025 | 31/12/2025 | 0 | Non démarré | Compliance
A015 | AI_APP | Consent flows & DSAR fulfillment | Hatem/Firas | 31/12/2025 | 15/01/2026 | 0 | Non démarré | Compliance
A016 | AI_APP | End-to-End encryption implementation | Hatem/Firas | 15/01/2026 | 31/01/2026 | 0 | Non démarré | Security
A017 | AI_APP | Cloud auto-scaling infrastructure | Hatem/Firas | 07/12/2025 | 22/12/2025 | 0 | Non démarré | Infrastructure
A018 | AI_APP | API rate limiting & monitoring | Hatem/Firas | 22/12/2025 | 31/12/2025 | 0 | Non démarré | Infrastructure
A019 | AI_APP | Daily backup system setup | Hatem/Firas | 22/12/2025 | 31/12/2025 | 0 | Non démarré | Infrastructure
A020 | AI_APP | Crash reporting integration | Hatem/Firas | 31/12/2025 | 15/01/2026 | 0 | Non démarré | Infrastructure
A021 | AI_APP | 50+ test cases development | Hatem | 15/01/2026 | 31/01/2026 | 0 | Non démarré | QA
A022 | AI_APP | 1000-user beta program (12 weeks) | Hatem/Firas | 01/02/2026 | 28/04/2026 | 0 | Non démarré | Testing
A023 | AI_APP | Device testing (10+ devices) | Hatem | 15/01/2026 | 31/01/2026 | 0 | Non démarré | QA
A024 | AI_APP | Accessibility testing (WCAG 2.1 AA) | Hatem/Nourey | 15/01/2026 | 31/01/2026 | 0 | Non démarré | QA
A025 | AI_APP | Offline/low bandwidth testing | Hatem | 22/01/2026 | 31/01/2026 | 0 | Non démarré | QA
A026 | AI_APP | iOS app development & submission | Hatem/Firas | 15/12/2025 | 07/02/2026 | 0 | Non démarré | iOS | Apple approval
A027 | AI_APP | Android app development & submission | Hatem/Firas | 15/12/2025 | 07/02/2026 | 0 | Non démarré | Android | Google approval
E001 | ECOMMERCE | eCommerce strategy & product mix | Farah/Nourey | 07/12/2025 | 22/12/2025 | 0 | Non démarré | Planning
E002 | ECOMMERCE | 50+ SKU product catalog creation | Nourey/Farah | 15/01/2026 | 07/02/2026 | 0 | Non démarré | Product
E003 | ECOMMERCE | Website eCommerce integration | Hatem/Firas | 15/01/2026 | 31/01/2026 | 0 | Non démarré | Website | Website launch
E004 | ECOMMERCE | Mobile checkout flow (app) | Hatem/Firas | 08/01/2026 | 31/01/2026 | 0 | Non démarré | App
E005 | ECOMMERCE | Payment gateway integration (2 min) | Hatem/Firas | 15/01/2026 | 31/01/2026 | 0 | Non démarré | Payments | PCI DSS
E006 | ECOMMERCE | Discount/promo system setup | Hatem/Firas | 01/02/2026 | 15/02/2026 | 0 | Non démarré | Features
E007 | ECOMMERCE | Order tracking system | Hatem/Firas | 01/02/2026 | 15/02/2026 | 0 | Non démarré | Features
E008 | ECOMMERCE | Customer support interface | Ismail/Hatem | 15/02/2026 | 28/02/2026 | 0 | Non démarré | Support
E009 | ECOMMERCE | Conversion analytics dashboard | Farah/Hatem | 22/02/2026 | 07/03/2026 | 0 | Non démarré | Analytics
E010 | ECOMMERCE | Apparel products (20+ items) | Nourey/Farah | 15/01/2026 | 31/01/2026 | 0 | Non démarré | Product
E011 | ECOMMERCE | Accessories products (15+ items) | Nourey/Farah | 15/01/2026 | 31/01/2026 | 0 | Non démarré | Product
E012 | ECOMMERCE | Collectibles products (10+ items) | Nourey/Farah | 22/01/2026 | 07/02/2026 | 0 | Non démarré | Product
E013 | ECOMMERCE | Digital items (5+ products) | Hamza/Hatem | 01/02/2026 | 15/02/2026 | 0 | Non démarré | Digital
E014 | ECOMMERCE | Season drops planning & execution | Farah/Nourey | 15/02/2026 | 28/02/2026 | 0 | Non démarré | Planning
E015 | ECOMMERCE | Collaboration drops planning | Farah/Nourey | 22/02/2026 | 07/03/2026 | 0 | Non démarré | Planning | Partner coordination